## Sheet1
| Internship Title | Cloud Intern
| Intern Name | Ghazi Mabrouki
| Department/Team | ICT Marketing & Solution Sales Dept
| Mentor | Ibrahim Arfaoui , Yan Zhong
| Supervisor | Ibrahim Arfaoui
| Start Date | 13/04/2026
| End Date | 17/04/2026
Overall Goals
| GOAL 1 | Ensure seamless frontend–backend integration
| GOAL 2 | Enhance system visibility and intelligence
| GOAL 3 | Build a PDF-to-Excel-to-PPTX pipeline for automated INT quarterly report generation.
| Tasks | Progress | Courses Learned (I-learning) | Difficulties Faced | Support Needed
Day 1 | Integrated frontend with backend APIs (alerts, incidents, dashboard, system health). Connected UI components to real data sources and ensured correct data flow. | Completed core API integration and verified endpoints connectivity. Frontend now displays real alerts and incidents dynamically. |  | Minor issues with endpoint mapping and 404 errors (routes mismatch), resolved by aligning frontend calls with backend routes. | Door access
Day 2 | Scaffold a PDF-to-Excel-to-PPTX pipeline and implement all three stages (extract, integrate, present). | Created project skeleton and scripts/stage1_extract.py (Kimi Vision API); built stage2_integrate.py (Excel column append) and stage3_present.py (12-slide PPTX with trend charts); fixed KPI and chart-series mappings end-to-end. |  | Chart series and column index derivation were hardcoded; resolved by deriving all indices from quarter labels in row 1. | Door access
Day 3 | Implemented IPS Map visualization showing real-time traffic between IP addresses and servers. Improved geolocation accuracy and filtered invalid IPs. Integrated AI Assistant and tested it on system-related queries (alerts, incidents, system behavior). | S map working with live traffic visualization. AI Assistant successfully answering contextual questions about system data. |  | Faced incorrect geolocation (fake coordinates issue) and AI context reset problem (stateless responses). Fixed by improving GeoIP logic and planning contextual memory handling. | Door access
Day 4 | Validate and finalize the end-to-end PDF-to-PPTX pipeline against real quarterly data. | Ran run_pipeline.sh against the TR2-2025 PDF; verified all KPI values match ground-truth anchors and confirmed 12-slide PPTX renders correct trend charts. |  | One chart slide rendered an empty series due to a trailing space in the quarter label; fixed by stripping whitespace during header parsing in stage2_integrate.py. | Door access
Day 5 | Plan to enhance system with better incident lifecycle management (archiving resolved incidents, improving visualization, and refining automation feedback loop). | Planned/In progress |  | — | Door access